## Plan
1. When to buy the domain name?
2. Do I need hire people design the webpage?
3. Do I need people help to work on English questions? Some questions could get from online, need people to review them. Need people design the test papers.
Phase 3 (2020/01/01 - 2020/12/30) : Start the TTM as a formal business
Time Start | 2020-01-01 | 2020-04-01 | 2020-07-01 | 2020-10-01 | 2021-01-01
Target | Move django to golang complete Release V 0.5 Because moving to golang, it was delaied 3 months | Complete AI Model-1 Complete Revise Model Release V 0.6 | Outsource English Question Release V 0.7 | Run on Android, ios Invite free user Release V 1.0 Updating and fix bugs | Release V1.1 Ready for TTM Sprint start from May to November | Comercial version online V 2.0
Month | 3 | 3 | 3 | 3 | 4 | 8 | 8
Status
Task | . Build ttm-go server . Update quasar . Updating question, fix bugs . Re-design assignment based on KP (Knowledge Point) . EA, EB need run. . Complete Report page . Continue work on Math Topics (MD, ME, MF, MG) | . Auto sending email function . keep update Topics . AI model . Revise strategy . Move to postgresql container . Complete the requirement docs of the web pages | . Redesign the web pages from out side designer, Need it for PC, Pad and Phone. . Complete Math . English Learning model . Find teachers review the questions and learning model . Generate (PDF) weekly report | . Redesign the web pages from out side designer, Need it for PC, Pad and Phone. . Complete Math . English Learning model . Find teachers review the questions and learning model . Generate (PDF) weekly report | . Complete Web design . Outsource test paper design . Oursource English questions? . Add payment function . Testing the web . Need complete 50% English . Release free account to Antrim Primary School | . Release free account to 10 school, should cover about 1000 pupils . Find out side profesional to evaluate the learning model . Update by feedback | . Find out what time in a year is the best time for Ads . After have 200 active users, start looking for investor . Need CEO, COO, Python engineer and teachers Need cover 5k - 20k student, i.e. 3% - 10% student. This will give us the real data about everything. Release V 1.*
Phase 2 (2019/04/01 - 2019/09/30): Complete Model, Math, part of English, all the web pages
Time Start | 2019-04-01 | 2019-04-29 | 2019-05-20 | 2019-06-17 | 2019-07-29 | 2019-09-23
Weeks | 4 | 4 | 4 | 6 | 8 | 10
Target |  |  |  | Re-design the topics and tasks Release V 0.3 | Using Vue.js as front-end frame and Django Graphql as back-end Release V 0.4 | Complete most development of Math. Back-end is ready Release V 0.5 Because move to golang, everything was rewrite
Status | Done |  |  | Done
Task | 1. Update A1, A3 questions 2. Add result page for review the result 3. Add IA app for data analysis 4. Add Fraction /Decimal Grade 1,2,3 in A2 (Part) | 1. Add login system (Done) 2. Use tool to insert questions into sqlite database (Done) 3. Complete A1, A3 questions (almost) 4. Student page (home, result, assignment)(done) 5. Mentor pages (result, report, add etc) 6. Function to update grade score(done) | 1. Release with login system includes: A1, A3, part of A2, A4 2. Add more questions A8 Roma number, Average, Percentage. 3. Find a way to add word problem A6, Use shanghai project 3 doc as an example. 4. Deal with wrong question 5. Update evaluation mechanism 6. Add sticker page | 1. Design Learning Model 2. Re-design Topics, make learn curve more flat. It needs to face the fresh P3 students. 3. Match topic/grade to the curriculum 4. English, add Plural Nouns words. (visit myEnglishPage.com) | 1. Continue work on Math Topics (MD, ME, MF, MG) 2. Update learning map and add revise stratagy. 3. Switch to DRF and Vue.js 4. Using paper.js for drawing 5. Start work on English works, grammar etc. Using 1000words.doc as an example source. 6. English, add Plural Nouns words. (visit myEnglishPage.com) | 1. Complete Learning Model 2. Re-design levels 3. EA, EB need run. 4. Complete the requirement docs of the web pages 5. Auto sending email 6. Buy domain name, set server 7. Add revise strategy 8. Complete message page 9. Complete Report page 10. Continue work on Math Topics (MD, ME, MF, MG)
Phase 1 (2018/11/01 - 2019/03/30): research and original design
Time Line
Weeks | 4 | 4 | 4 | 4 | 4
Status | Done | Done | Done | Done | Done
Task | 1. Research web technology 2. Learn open source projects from github | 1. Build example website from template | 1. Write python program to generate questions A1 2. Use tool to insert questions into sqlite database | 1. Add more questions 2. Learn questions from Kumon | 1. Run my website online, pythonanywhere for free 2. First release for users

## AI Model
Evaluate Result
|  |  |  | first perc | std | avg time |  | score |  |  | first perc | std | avg time | score
Steps |  |  |  | 50 | 16 | 26 | 0.61538 | 30.7692 | 31 |  | 69 | 16 | 26 | 0.61538 | 42.4615 | 31
1 | Get current practice paper log, remove highest 10 % and lowest 10% by time | Done in client side |  | 52 | 16 | 25 | 0.64 | 33.28 | 31.57 |  | 72 | 16 | 25 | 0.64 | 46.08 | 34.77
2 | Calculate average time of this paper | Done in client side |  | 54 | 16 | 24 | 0.66667 | 36 | 32.6775 |  | 89 | 16 | 24 | 0.66667 | 59.3333 | 40.9108
3 | Compare the STD time, get percentage | Perc = avg_time / STD time |  | 56 | 16 | 23 | 0.69565 | 38.9565 | 34.2473 |  | 90 | 16 | 23 | 0.69565 | 62.6087 | 46.3353
4 | Compare to the previous average time in the same topic, get percentage | Perc1 = avg_time/ avg_time_pre |  | 58 | 16 | 22 | 0.72727 | 42.1818 | 36.2309 |  | 92 | 16 | 22 | 0.72727 | 66.9091 | 51.4787
5 | Update avg_pre_time |  |  | 60 | 16 | 21 | 0.7619 | 45.7143 | 38.6017 |  | 90 | 16 | 21 | 0.7619 | 68.5714 | 55.7519
6 | Compare to previous first_perc, get percentage | Perc2 = first_perc / first_perc_pre |  | 62 | 16 | 20 | 0.8 | 49.6 | 41.3513 |  | 90 | 16 | 16 | 1 | 90 | 64.3139
7 | std time / avg time > 0.7 first perc > 0.9, then PASS When PASS 3 times consecutively, set MASTER_1 (Need rework) |  |  | 64 | 16 | 19 | 0.84211 | 53.8947 | 44.4872 |  | 92 | 16 | 15 | 1.0667 | 98.1333 | 72.7688
| std time / avg time > 1 first perc > 0.9, three times consecutively, set MASTER_2 (don't need rework) |  |  | 66 | 16 | 18 | 0.88889 | 58.6667 | 48.032 |  | 90 | 16 | 14 | 1.1429 | 102.8571 | 80.2909
|  |  |  | 68 | 16 | 17 | 0.94118 | 64 | 52.024
|  |  |  | 70 | 16 | 16 | 1 | 70 | 56.518
|  |  |  | 72 | 16 | 15 | 1.0667 | 76.8 | 61.5885
|  |  |  | 74 | 16 | 14 | 1.1429 | 84.5714 | 67.3342
|  |  |  | 76 | 16 | 13 | 1.2308 | 93.5385 | 73.8853
|  |  |  | 78 | 16 | 12 | 1.3333 | 104 | 81.414
|  |  |  | 80 | 16 | 11 | 1.4545 | 116.3636 | 90.1514
|  |  |  | 82 | 16 | 10 | 1.6 | 131.2 | 100.4135
|  |  |  | 84 | 16 | 9 | 1.7778 | 149.3333 | 112.6435
|  |  |  | 86 | 16 | 8 | 2 | 172 | 127.4826
|  |  |  | 88 | 16 | 8 | 2 | 176 | 139.612
|  |  |  | 90 | 16 | 8 | 2 | 180 | 149.709
|  |  |  | 92 | 16 | 8 | 2 | 184 | 158.2817
|  |  |  | 94 | 16 | 8 | 2 | 188 | 165.7113
|  |  |  | 96 | 16 | 8 | 2 | 192 | 172.2835
|  |  |  | 98 | 16 | 8 | 2 | 196 | 178.2126
|  |  |  | 100 | 16 | 8 | 2 | 200 | 183.6595
|  |  | std time | correct | std/10 | correctPercent > 85, time ok | first 3 times or correct per < 85 and > 60 | increament | number of questions | total time | number of questions, after 3 times
|  |  | 4 | 1 | 0 | 1 |  | 2 | 50 | 200 | 50 | 200 | 400
|  |  | 8 | 1 | 1 | 1 |  | 3 | 33 | 264 | 33 | 264 | 528
|  |  | 12 | 1 | 1 | 1 | 1 | 4 | 25 | 300 | 33 | 396 | 792
|  |  | 16 | 1 | 2 | 1 | 1 | 5 | 20 | 320 | 25 | 400 | 800
|  |  | 20 | 1 | 2 | 1 | 1 | 5 | 20 | 400 | 25 | 500 | 1000
|  |  | 24 | 1 | 2 | 1 | 1 | 5 | 20 | 480 | 25 | 600 | 1200
|  |  | 28 | 1 | 3 | 1 | 1 | 6 | 17 | 476 | 20 | 560 | 1120
|  |  | 32 | 1 | 3 | 1 | 1 | 6 | 17 | 544 | 20 | 640 | 1280
|  |  | 36 | 1 | 4 | 1 | 1 | 7 | 14 | 504 | 17 | 612 | 1224
|  |  | 40 | 1 | 4 | 1 | 1 | 7 | 14 | 560 | 17 | 680 | 1360
|  |  | 50 | 1 | 5 | 1 | 1 | 8 | 13 | 650 | 14 | 700 | 1400
|  |  | 60 | 1 | 6 | 1 | 1 | 9 | 11 | 660 | 13 | 780 | 1560

## Topics A
The whole system has 6 stages, reflect to Year 1 to 6. In each stage, there are three levels, so totally it has 18 levels for each topic In the database, it only has 18 grades
| Grade | Topic_A1: Basic Calculation | Topic_A2: Decimal/ Fraction | Topic_A3: Algebra | Topic_A4: Measurement | Topic_A5: 2-D, 3-D Shape | Topic_A6: Application Problem | Topic_A7: Graph | Topic_A8: Misc
| 1 | PM, two numbers less than 30 | Decimal Concept (read, write) | x + 5 = 10, learn concept 1 | Time - easy | Learn Shape name -easy | Place of the Number less 100 | Column graphs | number places, more/less, patterns
| 2 | PM, three number less than 12 | Decimal PM - easy | 2 *x = 50, learn concept 2 | Time - hard | Learn More Shape name -hard | Number Plus and Minus | Pie charts | Roma Number
| 3 | Plus, two numbers, column method - easy | Decimal PM - hard | (2 + x) + 50 = 100, concept 3 | Money -easy (then move to A6 Money) | Count Shape in a picture | Write numbers in words | Co-ordinates | Average
| 4 | Plus, two or three number, column method - hard | Decimal TD - easy | mix pmtd, bracket, concept 4 | units - easy (length, weight, lilte) |  |  | Reflection and Rotation | Percentage
| 5 | Minus, two big numbers, column method - easy | Decimal TD - hard | two x, integer - easy | units - hard (perimeter, area, volume) This mixed with Shapes |  |  | Nets of shapes | ratio, propotion
| 6 | Minus, two big numbers, column method - hard | Decimal Mixed (bracket, minus) - easy | two x, integer - hard | distance, speed, time | Area, paremeter |  | Marking and interpreting scales | Prime numbers
| 7 | three numbers PM, mental work, less than 30 | Decimal Mixed (bracket, minus) - hard | one x, decimal - easy | Angle -easy | volume,cube and cuboids |  |  | highest common factor (or greatest common divisor, GCD) least common multiple
| 8 | Times Table 12 x 12 | Fraction Concept, read fraction, order fractions, comparison etc. | two x, decimal - hard | Angle - hard
| 9 | Division within times table | Fraction PM - easy | one x, fraction - easy
| 10 | one digital number times two digitals number, mental work - easy | Fraction PM - hard | two x, fraction - hard
| 11 | two digital number times two digitals number, column method - hard | Fraction TD - easy | one x, minus number - easy
| 12 | two digital number divided by one digital number with remainder - easy | Fraction TD - hard | two x, minus number - hard
| 13 | two or three digitals number divided by two digitals number with remainder -hard | Fraction Mixed - easy | mix all - easy
| 14 | P.M.T.D rules - easy | Fraction Mixed - hard | mix all - hard
| 15 | P.M.T.D rules - hard | Fraction, decimal mixed - easy | system equation - easy
| 16 | bracket - easy | Fraction, decimal mixed - hard | system equation - hard
| 17 | bracket - hard |  | system equation x, y, z - hard
| 18 | minus number - easy |  | system equation fraction,decimal
| 19 | minus number - hard
| 20 | mixed all - easy
| 21 | mixed all - hard
1. The assignment is based on specific topic. Which means in the same day, you always work on the same topic, this reinforce and solid the knowledge you learnt. The topic will switch based on AI, for a topic, you may work on one day or one week. 2. In each topic, we log the score of it before you move to the next topic. the topic will be repeat until you pass all grades. 3. in each topic, you will have a review day that repeat the failed questions from the previous topic. 4. each topic works on their own way, ig. on some topic you go to master, some topics still medium.

## Topics B
The whole system has 6 stages, reflect to Year 1 to 6. In each stage, there are three levels, so totally it has 18 levels for each topic In the database, it only has 18 grades
| Grade | Topic_B1: Vercabulary | Topic_B2: Grammar | Topic_B3: Punctury | Topic_B4: Comprehensive
| 1 | vercabulary - 1, basic from P1, P2, P3 | Tense - present tense, past tense, future tense - easy
| 2 | vercabulary - 2, middle level from P4, P5 | Tense - practice in sentences - easy
| 3 | vercabulary - 3, from P6, P7 | Tense - present tense, past tense, future tense - hard
| 4 | vercabulary - 4, extended level | Tense - practice in sentences - hard
| 5 |  | Plurality table - easy
| 6 |  | Plurality practice - easy
| 7 |  | Plurality table - hard
| 8 |  | Plurality practice -hard
9
10
11
12
13
14
Mock Test | 15
16
17
18
1. The assignment is based on specific topic. Which means in the same day, you always work on the same topic, this reinforce and solid the knowledge you learnt. The topic will switch based on AI, for a topic, you may work on one day or one week. 2. In each topic, we log the score of it before you move to the next topic. the topic will be repeat until you pass all grades. 3. in each topic, you will have a review day that repeat the failed questions from the previous topic. 4. each topic works on their own way, ig. on some topic you go to master, some topics still medium.

## Ideas
|  |  | Selected? | Implemented?
1 | Try different strategy of the practice, AI choose the questions from different topics, 2 or 3 then make up a practice paper. The student need to finish all the questions each day, rather than count time and score. could be two mode: Learning mode (no timer) and practice mode (with timer) | This can be used as revise mode. i.e. learning mode only run single task; revise mode run mixed previous tasks
Benefit: | 1. Student only do two papers each day, one Math, one English 2. The paper mixed different type of questions, just like Shanghai project 3. Each question has the STD time with it, could used for calculation at client side
Drawback: | 1. Current evaluation system based on the Time and correct percentage, does it fit in this method? 2. When log the wrong questions or passed questions, does it make it more difficult? 3. Cannot log the paper under topic anymore. But we can log then under topic as How many questions you have done, and what is time and perc. This should works. 4. From efficiency view, Specific Topic traning may more efficient. Mixed questions may distruct student. 5. Different questions type may need run different HTML.
2
3 | How to do the revise? By time, like revise the topic after complete 5, 10, 15, 20 days? How long to complete a topic? | pupils has two tasks, ig. 1 and 3; 2 and 4;
4 | Do we need do a test every week? Using Mixed questions from previous practice? Do a test every Month?
5 | Regards of the learning stages. The whole process need to be splitted to some stages / milestones. The milestones was defined follow the curriculum, so at each milestone, Mentor will be clearly know where the student is. To pass the milestone, students need complete requiered ST, and do several tests. There should be some kind of reward for it. And make sure that when we say the student pass P4 level, he should be definitely above P4 level. This will give the Mentor/parent the confidence of our system, because we have the higher standard than others. | Set 10 levels, each level includes some tasks from all the topics.
6 | Do we need to make TTM Tablet? 90% UK house has Internet, so most parent don't need stand alone Learning Pad. But sell a good quality Tabet could help student learning easily because not all the parent has the computer for Children. Children are very easy to be distracted Portable, could do the work out of the home (using Phone?) | It needs proper software on tablet, need tablet, maintaining etc.
7 | Need a repeat mechanism, for example, when learn new words, we pick up 10 words and repeat it 5 times to make a task
8 | Need log which question passed, and which one not. When learn new words, we take 20 new words each time, if failed, log the ID and set a counter to 3. Next time will take these failed words and plus some new words. If passed, counter -1, so after 3 times passed, remove it from wrong list. To trace the question ID to find out where we are, it need remember the ID head and tail. 1. Make question randomly before saved in database, so when get question by ID, they are random questions. The questions were repeat in a loop, so make sure every question will be touched. If target is do 100 questions each task, make sure there are 500 questions for each topic set. 2. For each topic set, based on the number of questions, split into 3 subsets. Get questions randomly in each subset, when one subset passed, go to the next subset.
9 | How to learn new English words? Each time show 4 pic with description and tip, ask pupil input the words, do it 10 each day, 3 times. Moving forword depends on student's performance. Note that total words round 10K, if we aim to learn all of them before P7, we have only 5 years, i.e. 2000/year or 5.5/day Need add reading part, which will be a short paragragh around 100 words. By online research, student need around 7k words to cover 95% common reading. So we need 10k words from github as the base, compare with other lists, make it fully covered all the words. The words was split 10 grades, each one has 1000 words. | Need more details design
10 | The update_score function need consider the level of the pupil. At the begainning, should give more time, and reduce time depends on the Proficiency. Which means we need log the proficiency of the each task. It could a value in task score, or we have proficiency level for each task. Once we have AI model to calculate the score, we could see if it could be used for this purpose. Basically, they are the same thing that is evalue how the pupil master the task.
11 | 1. When pupil do a task at the first time, it move like evaluation phase. So we let pupil do either 12 mins or 35 - 50 questions, then finish it. 2. AI module do evaluation and set a score for each task. The score under 40 means pupil is not ready to do this level; above 100 means PASS this level but still need revise later; above 150 means MASTER, don't need revise any more. 3. The score for a task determine the std time for next task working. This solve the problem that different pupil have different level, but they need complete the task at a proper time. 4. The task was switched between topic every 3 completed tasks. If it is not PASS, we will loop it back for this topic. 5. pupil may go faster on some topics then others, AI should balance those topics, if we set 6 levels, the gap between fastest and lowest should not be more than 2. 6. Each pupil need have their own log book for each task, just a json object like ["MA1": 120, "count": 7], AI module holding the Levels and decided which task be assigned on the next one. | 1. How to evaluate and set score? 2. How to use score as reference to set STD? 3. How to split topics in 6 levels? Maybe more, like 10? During implementation and using by Lucas and Jamie, this strategy not work very well. The updated version is on going
12 | Need set up a upgrade system, give the pupil the level just like play game. This can be done by how many tasks PASS or By how much score in total Give a award for each PASS task The award system could be 1. Each time complete whold homework, give a sticker 2. Each time PASS a task, give a golden coin 3. PASS each level, give milestone badge | The Implementation will be make a RPG game, pupil collect score, sticker, stars from the daily work and could use those stuff in the game. For example, SCORE could be the money to buy anything. STICKER could be used to buy special equipment; STAR could be used for level up
13 | Add task revise, this could be the same way as Evaluation, but should include most previous tasks
14
15 | When using coin to play game, provide Math Chellange to earn more coins | Thinking about game later. The main thing is to make a good game, we need a whole separate team, before we have enough profit, it is too risky to do it.
16 | we provide sprint course specific for p7/y6 student, one year sprint course | For many people cannot keep learning for long time, they may just want sprint at the last year, this includes the weekly mock test, adjust assignment based on the mock test etc. This could be extra service or a separate service.
17 | Mock test run 6 month, combined with above idea, it could be an separate service. For non-membership user, they could only pay for this sprint course. | Golden badge -free (complete 80% tasks) Silver badge - pay 10 ( Complete 60% tasks) Brown badge - pay 20
18 | The yearly price should be as less as possible Based on current research, reasonable price should be 60 - 90 / year Then we probably set 29/ year (2.4/month) As it is not a one time payment, people may keep using it three or four years, to keep them in is more important | From my model, the best profit price is 45, we may set it to 38? As the target paied rate is 0.5%, see the table on the right. |  |  | Paied rate | NI | UK | EU |  | month1 |  |  | 38.9/year or month 2 |  |  | 45/year or month 3 |  |  | 180@TTS
19 | Add function to review student's whole work, this is useful for the mentor if mentor managed many student and need to know the details performance of the students | should be as short and clear as possible, because we want save the time for mentor/parents |  | Pupils |  | 170000 | 4200000 | 20000000 |  | 4.89 |  |  | 3.24 |  |  | 3.75 |  |  | 30
20 | Add function to allow Teachers/Mentors/Parents add questions by themselves. We need professional teacher review and class those quesitons. If anyone contribute more than 50 used questions, allow them free membership for a month | Does it ok? Or this function only openned to prefessional Mentor/Teacher? For most parents, they use us just for save the time, so they probably don't like to input questions and it may cause the copyright issue if they use exist books for others |  |  | 0.005 | 850 | 21000 | 100000 |  | 4156.5 | 102690 | 489000 | 2754 | 68040 | 324000 | 3187.5 | 78750 | 375000 | 30600 | 756000 | 3600000
21 | We could provide service for professional mentor to create their own specific website, we design and maintain the website and using our QB. They just need help student when something need to teach. |  |  |  | 0.01 | 1700 | 42000 | 200000 |  | 8313 | 205380 | 978000 | 5508 | 136080 | 648000 | 6375 | 157500 | 750000 | 61200 | 1512000 | 7200000
22 | In the feature, we could provide 1 to 1 online teaching service, let mentor teach student online. This will work only after we have a lots of users, no matter paied or free users. | This means parents need monitor children to meet the teacher, it is agains our aim that is free parents. |  |  | 0.015 | 2550 | 63000 | 300000 |  | 12469.5 | 308070 | 1467000 | 8262 | 204120 | 972000 | 9562.5 | 236250 | 1125000 | 91800 | 2268000 | 10800000
23 | Set up live teaching video on specific topic, let student registers to watch. Some topics are for parents too, such as how to mentor your children; how to prepare the test etc. This could be a normal video or live, interactive video | as above, to let children sit there at specific time need extra work for parents. Need find out how much student / parents want do it. |  |  | 0.02 | 3400 | 84000 | 400000 |  | 16626 | 410760 | 1956000 | 11016 | 272160 | 1296000 | 12750 | 315000 | 1500000 | 122400 | 3024000 | 14400000
24 | We need hire part time teacher/workers, for example, some grammar school student, some uni students etc. The purpose is to let them use their spare time to contribut to the question bank. And we need professional part time teacher to review and evaluate those works. All the jobs are part time and pay for the time on working. | This is the way to keep company light; this is the way to use idea of share economic, we collect people's spare time and pay less. The pre-condition is we need have a mechenism to evaluation the workers. |  |  | 0.025 | 4250 | 105000 | 500000 |  | 20782.5 | 513450 | 2445000 | 13770 | 340200 | 1620000 | 15937.5 | 393750 | 1875000 | 153000 | 3780000 | 18000000
25 | Each word problem need have several tags, according to the testing points of the question. This tag should be as many as it can. If student make a wrong answer, we could combine those tags to find out what kind of question is the downside of the student. For example, if wrong questions with tag: time, average, speed and tag: time, divide; then we know the time probably is the problem for this student. | For specific learning, we don't need do this. But for word problem solving, it is a key for evaluation. |  |  | 0.03 | 5100 | 126000 | 600000 |  | 24939 | 616140 | 2934000 | 16524 | 408240 | 1944000 | 19125 | 472500 | 2250000 | 183600 | 4536000 | 21600000
26 | From the right table, if the target is 0.5% paid users, in NI it only support a company with 2 people In UK, the monthly income could be 320K, (24 times more than NI), this could support a 20 - 40 people company. So we have to go to England, the whole UK! Which means we need VR and NVR. | The rate is just guess now, we need real data to prove or show what it is. That's why we need do NI first, after 6 month, we will much more clear what it will be. Note: 2017 half of P7 students go to Transfer Test, i.e. 50% of 170k student has the requirement of improve their skills. If we got 10% of thess 50%, it will be 5% |  |  | 0.035 | 5950 | 147000 | 700000 |  | 29095.5 | 718830 | 3423000 | 19278 | 476280 | 2268000 | 22312.5 | 551250 | 2625000 | 214200 | 5292000 | 25200000
27 | How many family in UK has computer? Or most of them use Phone or Tablet? |  |  |  | 0.04 | 6800 | 168000 | 800000 |  | 33252 | 821520 | 3912000 | 22032 | 544320 | 2592000 | 25500 | 630000 | 3000000 | 244800 | 6048000 | 28800000
28 | Membership user could download questions for the next 7 days | This is useful if tablet cannot access Mobile network |  |  | 0.045 | 7650 | 189000 | 900000 |  | 37408.5 | 924210 | 4401000 | 24786 | 612360 | 2916000 | 28687.5 | 708750 | 3375000 | 275400 | 6804000 | 32400000
29 | Most parents don't want children using Phone or Computer for studying, the main reason is they cannot control what they do on it. | Release Study machine maybe a good idea? |  | China 2018 | 0.05 | 8500 | 210000 | 1000000 |  | 41565 | 1026900 | 4890000 | 27540 | 680400 | 3240000 | 31875 | 787500 | 3750000 | 306000 | 7560000 | 36000000
30 | What's the key points: 1. learning curve 2. Very fine knowledge points with cross match to let system know the student better them all the others 3. Positive response quick and strong, just like play RPG game 4. Fun learning steps, but not necessary for TTM Sprint. 5. TTM Spint need efficiency, let student and parents see the improvement clearly.
[9 empty] | 1000 | 5000 | 15000
[9 empty] | A | B | C
[7 empty] | Me | 70 | 59.5 | 53.55 | 48.195
[7 empty] | Em Pool | 15 | 12.75 | 11.475 | 10.3275
[7 empty] | Em1 | 8 | 6.8 | 6.12 | 5.508
[7 empty] | Em2 | 5 | 4.25 | 3.825 | 3.4425
[7 empty] | Em3 | 2 | 1.7 | 1.53 | 1.377
[9 empty] | 150 | 500 | 1500
[9 empty] | 165240 | 162 | 390

## otherWebs
|  |  | UK Ranking |  |  |  | Income
uk.IXL.com | Online learning system Online questions | 99/year (math,english) | Very Active (388@US) | 15M/month
https://www.pre-test.co.uk/ | 21 mock test | £55/3 test | 57457 | Out of date
www.bofa11plus.com | Save Web as pre-test.co.uk | 58/year | 7942 | 50k /month | 1666/day | 2000 customers? | 116000
bond11plus.co.uk | Online questions | 60/year | 2347 | 200k views/month
www.elevenplusmock.org.uk | mock test |  | 71410

## Sheet1
|  | 24 | 652
CEO |  | 1 | 60
CEO | Chef Education O | 1 | 60
VP | Manage Ads | 1 | 60
Consultanta | From GL, CEM | 2 | 60
MathManager |  | 1 | 50
EnglishManager |  | 1 | 50
NonVerbal M |  | 1 | 50
Verbal M |  | 1 | 50
Python Engineer |  | 4 | 160
Web Engineer |  | 3 | 12
Germany | First five covers 20 Million pupils | 2 | 10
Franch |  | 2 | 10
Italy |  | 2 | 10
Turkey |  | 2 | 10
Norther Ireland | 170 k primary pupils
about 590 Primary schools
England 5-10 | 4100 K, 16700 Primary schools
EU | 29100 k, top 5 have 20M |  |  |  |  | 85000 | 2250000
[5 empty] | 1/1000 | No pupil
|  |  |  | 90 | 1 | 85 | 2250 | 7650 | 202500
|  |  |  | 89 | 2 | 170 | 4500 | 15130 | 400500
|  |  |  | 88 | 3 | 255 | 6750 | 22440 | 594000
|  |  |  | 87 | 4 | 340 | 9000 | 29580 | 783000
|  |  |  | 86 | 5 | 425 | 11250 | 36550 | 967500
|  |  |  | 85 | 6 | 510 | 13500 | 43350 | 1147500
|  |  |  | 84 | 7 | 595 | 15750 | 49980 | 1323000
|  |  |  | 83 | 8 | 680 | 18000 | 56440 | 1494000
|  |  |  | 82 | 9 | 765 | 20250 | 62730 | 1660500
|  |  |  | 81 | 10 | 850 | 22500 | 68850 | 1822500
|  |  |  | 80 | 11 | 935 | 24750 | 74800 | 1980000
|  |  |  | 79 | 12 | 1020 | 27000 | 80580 | 2133000
|  |  |  | 78 | 13 | 1105 | 29250 | 86190 | 2281500
|  |  |  | 77 | 14 | 1190 | 31500 | 91630 | 2425500
|  |  |  | 76 | 15 | 1275 | 33750 | 96900 | 2565000
|  |  |  | 75 | 16 | 1360 | 36000 | 102000 | 2700000
|  |  |  | 74 | 17 | 1445 | 38250 | 106930 | 2830500
|  |  |  | 73 | 18 | 1530 | 40500 | 111690 | 2956500
|  |  |  | 72 | 19 | 1615 | 42750 | 116280 | 3078000
|  |  |  | 71 | 20 | 1700 | 45000 | 120700 | 3195000
|  |  |  | 70 | 21 | 1785 | 47250 | 124950 | 3307500
|  |  |  | 69 | 22 | 1870 | 49500 | 129030 | 3415500
|  |  |  | 68 | 23 | 1955 | 51750 | 132940 | 3519000
|  |  |  | 67 | 24 | 2040 | 54000 | 136680 | 3618000
|  |  |  | 66 | 25 | 2125 | 56250 | 140250 | 3712500
|  |  |  | 65 | 26 | 2210 | 58500 | 143650 | 3802500
|  |  |  | 64 | 27 | 2295 | 60750 | 146880 | 3888000
|  |  |  | 63 | 28 | 2380 | 63000 | 149940 | 3969000
|  |  |  | 62 | 29 | 2465 | 65250 | 152830 | 4045500
|  |  |  | 61 | 30 | 2550 | 67500 | 155550 | 4117500
|  |  |  | 60 | 31 | 2635 | 69750 | 158100 | 4185000
|  |  |  | 59 | 32 | 2720 | 72000 | 160480 | 4248000
|  |  |  | 58 | 33 | 2805 | 74250 | 162690 | 4306500
|  |  |  | 57 | 34 | 2890 | 76500 | 164730 | 4360500
|  |  |  | 56 | 35 | 2975 | 78750 | 166600 | 4410000
|  |  |  | 55 | 36 | 3060 | 81000 | 168300 | 4455000
|  |  |  | 54 | 37 | 3145 | 83250 | 169830 | 4495500
|  |  |  | 53 | 38 | 3230 | 85500 | 171190 | 4531500
|  |  |  | 52 | 39 | 3315 | 87750 | 172380 | 4563000
|  |  |  | 51 | 40 | 3400 | 90000 | 173400 | 4590000
|  |  |  | 50 | 41 | 3485 | 92250 | 174250 | 4612500
|  |  |  | 49 | 42 | 3570 | 94500 | 174930 | 4630500
|  |  |  | 48 | 43 | 3655 | 96750 | 175440 | 4644000
|  |  |  | 47 | 44 | 3740 | 99000 | 175780 | 4653000
|  |  |  | 46 | 45 | 3825 | 101250 | 175950 | 4657500
|  |  |  | 45 | 46 | 3910 | 103500 | 175950 | 4657500
|  |  |  | 44 | 47 | 3995 | 105750 | 175780 | 4653000
|  |  |  | 43 | 48 | 4080 | 108000 | 175440 | 4644000
|  |  |  | 42 | 49 | 4165 | 110250 | 174930 | 4630500
|  |  |  | 41 | 50 | 4250 | 112500 | 174250 | 4612500
|  |  |  | 40 | 51 | 4335 | 114750 | 173400 | 4590000
|  |  |  | 39 | 52 | 4420 | 117000 | 172380 | 4563000
|  |  |  | 38 | 53 | 4505 | 119250 | 171190 | 4531500
|  |  |  | 37 | 54 | 4590 | 121500 | 169830 | 4495500
|  |  |  | 36 | 55 | 4675 | 123750 | 168300 | 4455000
|  |  |  | 35 | 56 | 4760 | 126000 | 166600 | 4410000
|  |  |  | 34 | 57 | 4845 | 128250 | 164730 | 4360500
|  |  |  | 33 | 58 | 4930 | 130500 | 162690 | 4306500
|  |  |  | 32 | 59 | 5015 | 132750 | 160480 | 4248000
|  |  |  | 31 | 60 | 5100 | 135000 | 158100 | 4185000
|  |  |  | 30 | 61 | 5185 | 137250 | 155550 | 4117500
|  |  |  | 29 | 62 | 5270 | 139500 | 152830 | 4045500
|  |  |  | 28 | 63 | 5355 | 141750 | 149940 | 3969000
|  |  |  | 27 | 64 | 5440 | 144000 | 146880 | 3888000
|  |  |  | 26 | 65 | 5525 | 146250 | 143650 | 3802500
|  |  |  | 25 | 66 | 5610 | 148500 | 140250 | 3712500
|  |  |  | 24 | 67 | 5695 | 150750 | 136680 | 3618000
|  |  |  | 23 | 68 | 5780 | 153000 | 132940 | 3519000
|  |  |  | 22 | 69 | 5865 | 155250 | 129030 | 3415500
|  |  |  | 21 | 70 | 5950 | 157500 | 124950 | 3307500
|  |  |  | 20 | 71 | 6035 | 159750 | 120700 | 3195000
|  |  |  | 19 | 72 | 6120 | 162000 | 116280 | 3078000
|  |  |  | 18 | 73 | 6205 | 164250 | 111690 | 2956500
|  |  |  | 17 | 74 | 6290 | 166500 | 106930 | 2830500
|  |  |  | 16 | 75 | 6375 | 168750 | 102000 | 2700000
|  |  |  | 15 | 76 | 6460 | 171000 | 96900 | 2565000

## bofa.com
This website do online test only It provide solution for any question So student will learn what's wrong with their mistakes Key Points: 1. It is NOT the practice homework, not everyday work as well 2. It doesn't have any learning curve mangement 3. You could buy monthly or yearly, but for testing, people don't need buy a year, so selling the tests maybe more reasonable. 4. Website design is not very interactive 5. Learn from them how to do the English stuff
31560
| Math | 9600
| English | 9600
| VR | 2520
| NVR | 2160
| Spelling | 2280
| Arithmetic | 5400

## Sheet4
http://www.adamsgs.org.uk/ ,Adams Grammar School
http://www.alcestergs.co.uk/page/default.asp?title=Home&amp;pid=1 ,Alcester Grammar School
http://www.agsb.co.uk/ ,Altrincham Grammar School for Boys
http://www.aggs.trafford.sch.uk/?page=admissions ,Altrincham Grammar School for Girls
http://www.ags.bucks.sch.uk/ ,Aylesbury Grammar School
http://www.ahs.bucks.sch.uk/ ,Aylesbury High School
http://www.brgs.org.uk/ ,Bacup and Rawtenstall Grammar School
http://www.bartoncourt.org/ ,Barton Court Grammar School
http://www.beaconsfieldhigh.bucks.sch.uk/ ,Beaconsfield High School
http://www.belfasthigh.org.uk/ ,Belfast High School
https://www.beths.bexley.sch.uk/beths/ ,Beth&#39;s Grammar School
http://www.bexleygs.co.uk/ ,Bexley Grammar School
http://www.bvgs.co.uk/ ,Bishop Vesey&#39;s Grammar School&nbsp;
http://www.bws-school.org.uk/ ,Bishop Wordsworth&#39;s School
http://website.bordengrammar.kent.sch.uk/ ,Borden Grammar School
http://www.bostongrammarschool.co.uk/ ,Boston Grammar School
http://www.bostonhighschool.co.uk/ ,Boston High School for Girls
http://www.bourne-grammar.lincs.sch.uk/ ,Bourne Grammar School
http://www.bournemouth-school.org/ ,Bournemouth School
http://bsg.bournemouth.sch.uk/ ,Bournemouth School for Girls
http://www.burnhamgrammar.org.uk/ ,Burnham Grammar School
http://www.busheymeads.org.uk/?option=com_content&amp;task=blogcategory&amp;id=46&amp;Itemid=110 ,Bushey Meads School
http://www.caistorgrammar.com/ ,Caistor Grammar School
http://www.caldaygrangegrammarschool.co.uk/page/default.asp?title=Home&amp;pid=1 ,Calday Grange Grammar School
http://www.carres.lincs.sch.uk/site/default.asp ,Carre&#39;s Grammar School
http://www.ceciljonesacademy.org.uk/home ,Cecil Jones College
http://www.chathamgirlsgrammar.medway.sch.uk/ ,Chatham Grammar School for Girls
http://www.ccgrammarschool.co.uk/ ,Chatham and Clarendon Grammar School
http://www.cchs.co.uk/ ,Chelmsford County High School for Girls
http://www.cheshamgrammar.org/ ,Chesham High School
http://www.csgrammar.com/ ,Chislehurst and Sidcup Grammar School&nbsp;&nbsp;
http://www.churstongrammar.com/ ,Churston Ferrers Grammar School
http://www.crgs.org.uk/ ,Clitheroe Royal Grammar School
http://cchsg.com ,Colchester County High School for Girls
http://www.crgs.co.uk/ ,Colchester Royal Grammar School
http://www.colytongrammar.devon.sch.uk/admissions/index.htm ,Colyton Grammar School
http://www.cranbrookschool.co.uk/ ,Cranbrook School
http://www.crossleyheath.org.uk/ ,Crossley Heath School
http://danecourt.kent.sch.uk/ ,Dane Court Grammar School
http://www.dartfordgrammarschool.org.uk/ ,Dartford Grammar School for Boys
http://www.dartfordgrammargirls.kent.sch.uk/ ,Dartford Grammar School for Girls
http://www.dhsb.org/ ,Devonport High School for Boys
http://www.devonportgirls.plymouth.sch.uk/ ,Devonport High School for Girls
http://www.dovergramboys.kent.sch.uk ,Dover Grammar School for Boys
http://dggs.kent.sch.uk/ ,Dover Grammar School for Girls
http://www.challoners.com/ ,Dr Challoner&#39;s Grammar School
http://www.challonershigh.com/page/default.asp?title=Home&amp;pid=1 ,Dr Challoner&#39;s High School
http://www.ermysteds.n-yorks.sch.uk/homepage.htm,Ermysted&#39;s Grammar School&nbsp; &nbsp; &nbsp;
http://www.folkestonegirls.kent.sch.uk/,Folkestone School for Girls
http://fortpitt.medway.sch.uk/new/ ,Fort Pitt Grammar School
http://gravesendgrammar.eu/,Gravesend Grammar School for Boys
http://www.mgsg.kent.sch.uk/ ,Mayfield Grammar School (Gravesend Grammar School for Girls)
http://www.greenshaw.co.uk/ ,Greenshaw High School
http://www.handsworth.bham.sch.uk/?option=com_content&amp;view=article&amp;id=125&amp;Itemid=165 ,Handsworth Grammar School
http://www.heckgrammar.co.uk/online/ ,Heckmondwike Grammar School
http://www.herschel.slough.sch.uk/ ,Herschel Grammar School
http://www.hsfg.org/ ,High School for Girls
http://www.highsted.kent.sch.uk/ ,Highsted School
http://www.highworth.kent.sch.uk/ ,Highworth Grammar School for Girls
http://www.ichs.org.uk/ ,Ilford County High School for Boys&nbsp;
http://www.invicta.viat.org.uk/ ,Invicta Grammar School
http://www.jhgs.bucks.sch.uk/ ,John Hampden Grammar School
http://www.kendrick.reading.sch.uk/ ,Kendrick School
http://www.kestevengrantham.lincs.sch.uk/ ,Kesteven and Grantham Girls&#39; School
http://www.kshs.uk/site/default.asp ,Kesteven and Sleaford High School
http://www.keaston.bham.sch.uk/ ,King Edward VI Aston School
http://kechg.org.uk/ ,King Edward VI Camp Hill Girls&#39; School
http://www.camphillboys.bham.sch.uk/ ,King Edward VI Camp Hill School (Boys)&nbsp; &nbsp;
http://www.kefw.org/ ,King Edward VI Five Ways School
http://www.kegs.org.uk/ ,King Edward VI Grammar School&nbsp;Essex
http://www.kes.net/ ,King Edward VI Grammar School&nbsp;Stratford
http://www.kingedwardvi.bham.sch.uk/ ,King Edward VI Handsworth School
http://www.king-edward.lincs.sch.uk/ ,King Edward VI Humanities College
http://joinus.kes.hants.sch.uk/ ,King Edward VI School
http://www.lggs.org.uk/ ,Lancaster Girls&#39; Grammar School
https://www.lrgs.org.uk/lancaster-royal-grammar-school ,Lancaster Royal Grammar School
http://www.lgs.slough.sch.uk/ ,Langley Grammar School
http://www.lawrencesheriffschool.net/ ,Lawrence Sheriff School
http://www.loretogrammar.co.uk/205/year-7 ,Loreto Grammar School
http://www.mgs.kent.sch.uk/community/parents/application-information/ ,Maidstone Grammar School
http://www.mggs.org/ ,Maidstone Grammar School for Girls&nbsp;
http://www.marling.gloucs.sch.uk/ ,Marling School
http://www.bromptonacademy.org.uk/105/admission-arrangements-for-new-year-7-students ,New Brompton College&nbsp;(Brompton Academy)
http://www.nghs.org.uk/ ,Newport Girls&#39; High School
http://www.newsteadwood.bromley.sch.uk/ ,Newstead Woods School for Girls
http://www.nonsuchschool.org/ ,Nonsuch High School for Girls
https://www.opgs.org/school/Pages/admissions.aspx ,Oakwood Park Grammar School
http://www.parkstone.poole.sch.uk/ ,Parkstone Grammar School
http://www.parmiters.herts.sch.uk/admissions/ ,Parmiter&rsquo;s School
http://www.pates.gloucs.sch.uk/ ,Pate&#39;s Grammar School
http://www.phsg.org/admissions-11-exams ,Plymouth High School for Girls
http://www.poolegrammar.com/ ,Poole Grammar School
http://www.qegs.cumbria.sch.uk/ ,Queen Elizabeth Grammar School&nbsp; &nbsp;Cumbria&nbsp;
http://www.qegs.co.uk/ ,Queen Elizabeth&#39;s GM Grammar School&nbsp;Alford
http://www.qegs.lincs.sch.uk/ ,Queen Elizabeth&#39;s Grammar School&nbsp;Horncastle
http://www.queenelizabeths.kent.sch.uk/193/admissions?preview ,Queen Elizabeth&#39;s Grammar School&nbsp;Kent
http://www.qehs.lincs.sch.uk/ ,Queen Elizabeth&#39;s High School
https://www.qebarnet.co.uk/admissions_page ,Queen Elizabeth&#39;s School
http://www.qmgs.walsall.sch.uk/ ,Queen Mary&#39;s Grammar School
http://www.qmhs.org.uk/admissions ,Queen Mary&#39;s High School
http://www.queens.herts.sch.uk/ ,Queens&rsquo; School
http://new.rainhammark.com/ ,Rainham Mark Grammar School
http://www.readinggirls.reading.sch.uk/contact.html ,Reading Girls&#39; School
http://www.reading-school.co.uk/ ,Reading School
http://www.ribstonhall.gloucs.sch.uk/admissions/ ,Ribston Hall High School
http://www.rickmansworth.herts.sch.uk/685/admissions ,Rickmansworth School
http://www.ripongrammar.co.uk/ ,Ripon Grammar School
http://www.rgshw.com/ ,Royal Grammar School
http://www.rugbyhighschool.co.uk/ ,Rugby High School for Girls
http://www.salegrammar.co.uk/ ,Sale Grammar School
http://www.shoeburynesshigh.co.uk/ ,Shoeburyness High School
http://www.langton.kent.sch.uk/ ,Simon Langton Girls&#39; Grammar School&nbsp;&nbsp;
https://www.thelangton.org.uk/ ,Simon Langton Grammar School for Boys
http://www.sirhenryfloyd.bucks.sch.uk/ ,Sir Henry Floyd Grammar School
http://www.manwoods.co.uk/ ,Sir Roger Manwood&#39;s School
https://strschool.co.uk/admissions/ ,Sir Thomas Rich&#39;s School
http://www.swbgs.com/ ,Sir William Borlase&#39;s Grammar School
http://www.sgs.lincs.sch.uk/ ,Skegness Grammar School
http://www.northernstaracademies.org.uk/skipton-girls-school/home/ ,Skipton Girls&#39; High School
http://www.swgs.wilts.sch.uk/defaultPage.asp?Page=100 ,South Wilts Grammar School for Girls
http://www.shsb.org.uk/page/default.asp?title=Home&amp;pid=1 ,Southend High School for Boys
http://www.shsg.org/ ,Southend High School for Girls
http://www.spaldinggrammar.lincs.sch.uk/ ,Spalding Grammar School
http://www.spaldinghigh.lincs.sch.uk/ ,Spalding High School
http://www.st-bernards.slough.sch.uk/admissions/ ,St Bernard&#39;s Catholic Grammar School
http://www.st-michaels.barnet.sch.uk/Pages/admissions.php ,St Michael&#39;s Catholic Grammar School
http://www.saintolaves.net/ ,St Olave&#39;s and St Saviour&#39;s Grammar School&nbsp;&nbsp;
http://www.st-ambrosecollege.org.uk/ ,St. Ambrose College
http://www.st-anselms.com/ ,St. Anselm&#39;s College
http://www.stbernardswestcliff.org.uk/ ,St. Bernard&rsquo;s High School and Arts College
http://www.st-thomasmore.southend.sch.uk/ ,St. Thomas More High School for Boys
http://www.sggs.org.uk/page/?title=Admissions&amp;pid=28 ,Stratford Upon Avon Grammar School for Girls
http://www.stretfordgrammar.com/admissions-menu/school-admission/ ,Stretford Grammar School
http://stroudhigh.gloucs.sch.uk/Admissions ,Stroud High School
https://www.suttcold.bham.sch.uk/scgsg/index.php ,Sutton Coldfield Girls&#39; School
http://www.suttongrammar.sutton.sch.uk/Admissions ,Sutton Grammar School for Boys
http://www.cryptschool.org/ ,The Crypt School
https://www.harveygs.kent.sch.uk/ ,The Harvey Grammar School
http://www.hbschool.org.uk/ ,The Henrietta Barnett School
http://www.thehowardschool.co.uk/ ,The Howard School
http://www.hundredofhooacademy.co.uk/322/admissions ,The Hundred of Hoo School
http://frog.judd.kent.sch.uk/ ,The Judd School
http://www.kings.lincs.sch.uk/page/?title=Home&amp;pid=1 ,The King&#39;s School
http://www.latymer.co.uk/ ,The Latymer School
http://www.bluecoatschoolliverpool.org.uk/ ,The Liverpool Blue Coat School
https://www.nhgs.co.uk/ ,The North Halifax Grammar School
http://www.nks.kent.sch.uk/?page_id=323 ,The Norton Knatchbull School
http://www.robertnapier.org.uk/ ,The Robert Napier Foundation School
http://www.rochestergrammar.org.uk/ ,The Rochester Grammar School
http://www.royallatin.org/ ,The Royal Latin School
http://www.skinners-school.co.uk/ ,The Skinners&#39; School
http://www.thespirescollege.com/ ,The Spires&nbsp;College
http://www.thomasaveling.co.uk/ ,The Thomas Aveling School
http://www.tiffingirls.kingston.sch.uk/ ,The Tiffin Girls&#39; School
http://www.tiffinschool.co.uk/home.html ,Tiffin School
http://www.tgs.kent.sch.uk/ ,Tonbridge Grammar School for Girls&nbsp;
http://www.tbgs.co.uk/ ,Torquay Boys&#39; Grammar School
http://tggsacademy.org/ ,Torquay Girls&#39; Grammar School
http://www.townleygrammar.org.uk/ ,Townley Grammar School for Girls
http://www.twggs.kent.sch.uk/ ,Tunbridge Wells Girls&#39; Grammar School
http://www.twgsb.org.uk/ ,Tunbridge Wells Grammar School for Boys
http://www.uptoncourtgrammar.org.uk/ ,Upton Court Grammar School
http://www.uptonhallschool.co.uk/ ,Upton Hall School
http://www.urmstongrammar.org.uk/ ,Urmston Grammar School
http://www.wcgs-sutton.co.uk/ ,Wallington County Grammar School
http://www.wallingtongirls.sutton.sch.uk/ ,Wallington High School for Girls
http://www.watfordboys.org/ ,Watford Grammar School for Boys
http://www.watfordgrammarschoolforgirls.org.uk/ ,Watford Grammar School for Girls
http://www.wealdofkent.kent.sch.uk/ ,Weald of Kent Grammar School for Girls
http://www.westkirby-grammar.wirral.sch.uk/ ,West Kirby Grammar School for Girls
http://www.whsb.essex.sch.uk/ ,Westcliff High School for Boys
http://www.whsg.info/ ,Westcliff High School for Girls
https://www.westlands.org.uk/ ,Westlands School
http://www.wgsb.org.uk/ ,Wilmington Grammar School for Boys&nbsp;&nbsp;
http://www.gsgw.org.uk/ ,Wilmington Grammar School for Girls
http://www.wilsonsschool.sutton.sch.uk/ ,Wilson&#39;s School
http://www.wirralgrammarboys.com/ ,Wirral Grammar School for Boys
http://www.wirralgirls.co.uk/ ,Wirral Grammar School for Girls
http://www.wghs.org.uk/ ,Wolverhampton Girls&#39; High School
http://www.woodford.redbridge.sch.uk/ ,Woodford County High School for Girls
http://www.whs.bucks.sch.uk/ ,Wycombe High School